# Keural Vision Encoder — Project Plan & Timeline

Generated: May 13, 2026  |  Demo Target: June 10, 2026  |  Hardware: RTX 5090 (32 GB)

## Table 1 — Phase Overview

| Phase | Name | ETA | What Trains | Data | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Vision Encoder Training | Done ~May 16–17 | Full encoder (SigLIP+HCT+Sal) | CC3M + CC12M (~6.9M pairs) | ⏳ ~58% complete step ~45k/75k |
| 2A | Projector Alignment | ~May 17–24 | LevelAwareProjector + LoRA (q,v) | CC3M captions (caption predict) | ⬜ Ready to start after Phase 1 |
| 2B | Instruction Fine-tuning | ~May 24–31 | Projector + LoRA (q,k,v,o+MoE) | LLaVA-Instruct 150K (VQA) | ⬜ After Phase 2A |
| 3 | Document Understanding | Post June 10 | Vision enc + Projector + LoRA | Docling dataset (RAG team) | 📋 Planned (post-demo) |

## Table 2 — Success Criteria

| Phase | Metric | Target | Current (step ~45k) |
| --- | --- | --- | --- |
| 1 | Primary loss (SigLIP) | < 1.5 | ~1.70 ✓ trending down |
| 1 | CC3M R@1 (200 pairs) | > 8% | 1–2% (normal at 60%) |
| 1 | CC3M MedR (200 pairs) | < 70 | ~97–108 (improving) |
| 1 | Pooled embedding norm | < 2.0 | ~4.48 (needs to drop) |
| 1 | Saliency loss | Stable 4–6 | ~4.9–5.0 ✓ stable |
| 2A | Caption BLEU / loss | Loss < 2.0 | — (not started) |
| 2A | Manual caption test | Coherent text | — (not started) |
| 2B | VQA accuracy (LLaVA-val) | > 40% | — (not started) |
| 2B | "What is this?" answer | Correct noun | — (not started) |

## Table 3 — Day-by-Day Timeline (May 13 → June 10)

| Date | Phase | Activity | Notes |
| --- | --- | --- | --- |
| May 13 | 1 | Training running (~45k/75k) | ~30k steps remaining, ~83h left |
| May 14–15 | 1 | Training continues | Monitor: loss, sal, GPU temp |
| May 16–17 | 1 | Phase 1 completes (step 75k) | Run CC3M 200-pair eval + saliency viz |
| May 17 | 1→2A | Push checkpoint-75000 to HF | Update HF README with final metrics |
| May 17 | 2A | Launch train_projector.py | Check step/s speed first — determines 2A ETA |
| May 18–23 | 2A | Projector alignment training | 10k steps, CC3M captions, loss should drop to <2.0 |
| May 24 | 2A | Phase 2A complete | Manual test: upload image → get caption |
| May 24 | 2A→2B | Download LLaVA-Instruct-150K | from datasets import load_dataset (liuhaotian/...) |
| May 24 | 2B | Launch train_vlm.py | Build train_vlm.py if not done yet |
| May 25–30 | 2B | Instruction fine-tuning | Wider LoRA (q,k,v,o + MoE), VQA format |
| May 31 | 2B | Phase 2B complete | Test: "What is in this image?" → correct answer |
| Jun 1–2 | Int. | Integration testing | Run full pipeline: image → question → answer |
| Jun 3–5 | Int. | Build demo_vlm.py | Simple demo script for June 10 presentation |
| Jun 6–7 | Demo | Prepare demo materials | Saliency viz, retrieval metrics slides |
| Jun 8–9 | Demo | Dry run | Full demo rehearsal, fix any remaining issues |
| Jun 10 | DEMO | POC Presentation | Live VLM demo + architecture + metrics |

## Table 4 — Scripts & Commands Reference

| Phase | Script | Command | Purpose |
| --- | --- | --- | --- |
| 1 | train.py | nohup bash scripts/launch_training.sh | Phase 1 vision encoder training |
| 1 | eval_retrieval_cc3m.py | python3.10 scripts/eval_retrieval_cc3m.py --checkpoint outputs/run/checkpoint-75000 --n-pairs 200 | R@1/R@5/MedR eval |
| 1 | visualize_saliency.py | python3.10 scripts/visualize_saliency.py --checkpoint outputs/run/checkpoint-75000 | Saliency map visualization |
| 1 | gui_eval.py | python3.10 scripts/gui_eval.py | Browser-based checkpoint evaluator |
| 2A | train_projector.py | python3.10 scripts/train_projector.py --vision-ckpt outputs/run/checkpoint-75000 | Phase 2A projector training |
| 2A | train_projector.py | python3.10 scripts/train_projector.py ... --resume | Resume Phase 2A from checkpoint |
| 2B | train_vlm.py | (to build) | Phase 2B instruction fine-tuning |
| Demo | demo_vlm.py | (to build) | June 10 live demo script |

Note: Phase 2A ETA (May 17–24) assumes ~60s/step on RTX 5090 with 14.8B QLoRA. Verify actual step speed in first 10 minutes of training and adjust timeline accordingly. June 10 demo requires Phase 2B complete — 10-day buffer exists for Phase 2 delays.